## Scrummaster
SCRUMMASTER
SPRINT 1 : | Dedy Suhendra | (4 Hari)
SPRINT 2 : | Jimmy Yappeter | (3 Hari)
SPRINT 3: | Boby Hartanto | (3 Hari)
SPRINT 4: | Frenky Salim | (4 Hari)

## 1.1
Burnt Down Chart Sprint 1 - Hari pertama
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Pendahuluan |  | 10
Tenses (I) |  | 40
Tenses (II) |  | 40
Tenses (III) |  | 40
Tenses (IV) |  | 40
| Total = | 170 | 0 | 0 | 0

## 1.2
Burnt Down Chart Sprint 1 - Hari pertama
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Pendahuluan |  | 10 | 0
Tenses (I) |  | 40 | 30
Tenses (II) |  | 40 | 30
Tenses (III) |  | 40 | 30
Tenses (IV) |  | 40 | 30
| Total = | 170 | 120 | 0 | 0

## 1.3
Burnt Down Chart Sprint 1 - Hari Ketiga
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Pendahuluan |  | 10 | 0 | 0
Tenses (I) |  | 40 | 30 | 20
Tenses (II) |  | 40 | 30 | 20
Tenses (III) |  | 40 | 30 | 20
Tenses (IV) |  | 40 | 30 | 20
| Total = | 170 | 120 | 80 | 0

## 1.4
Burnt Down Chart Sprint 1 - Hari Ketiga
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Pendahuluan |  | 10 | 0 | 0 | 0
Tenses (I) |  | 40 | 30 | 20 | 0
Tenses (II) |  | 40 | 30 | 20 | 0
Tenses (III) |  | 40 | 30 | 20 | 0
Tenses (IV) |  | 40 | 30 | 20 | 0
| Total = | 170 | 120 | 80 | 0

## 2.1
Burnt Down Chart Sprint 2 - Hari Pertama
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Question Tag |  | 30
Conditional Sentence |  | 35
Passive Voice Part I |  | 30
Passive Voice Part II |  | 30
Passive Voice Part III |  | 30
Passive Voice Part IV |  | 30
Snythesis |  | 30
Many & Much |  | 20
Modal & Auxiliaries |  | 35
Degree of Comparison |  | 25
Preposition |  | 25
| Total = | 320 | 0 | 0

## 2.2
Burnt Down Chart Sprint 2 - Hari Kedua
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Question Tag |  | 30 | 10
Conditional Sentence |  | 35 | 20
Passive Voice Part I |  | 30 | 30
Passive Voice Part II |  | 30 | 30
Passive Voice Part III |  | 30 | 30
Passive Voice Part IV |  | 30 | 30
Snythesis |  | 30 | 20
Many & Much |  | 20 | 20
Modal & Auxiliaries |  | 35 | 35
Degree of Comparison |  | 25 | 25
Preposition |  | 25 | 25
| Total = | 320 | 275 | 0

## 2.3
Burnt Down Chart Sprint 2 - Hari Ketiga
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Question Tag |  | 30 | 10 | 0
Conditional Sentence |  | 35 | 20 | 0
Passive Voice Part I |  | 30 | 30 | 30
Passive Voice Part II |  | 30 | 30 | 30
Passive Voice Part III |  | 30 | 30 | 30
Passive Voice Part IV |  | 30 | 30 | 30
Snythesis |  | 30 | 20 | 0
Many & Much |  | 20 | 20 | 0
Modal & Auxiliaries |  | 35 | 35 | 0
Degree of Comparison |  | 25 | 25 | 25
Preposition |  | 25 | 25 | 25
| Total = | 320 | 275 | 170

## 3.1
Burnt Down Chart Sprint 3 - Hari Pertama
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Degree of Comparison |  | 25
Preposition |  | 25
Passive Voice Part I |  | 30
Passive Voice Part IV |  | 30
Concordance |  | 30
Elliptical Construction |  | 30
Subjunctive |  | 30
| Total = | 200 | 0 | 0

## 3.2
Burnt Down Chart Sprint 3 - Hari Kedua
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Degree of Comparison |  | 25 | 0
Preposition |  | 25 | 25
Passive Voice Part I |  | 30 | 30
Passive Voice Part IV |  | 30 | 0
Concordance |  | 30 | 30
Elliptical Construction |  | 30 | 30
Subjunctive |  | 30 | 0
| Total = | 200 | 115 | 0

## 3.3
Burnt Down Chart Sprint 3 - Hari Ketiga
Sprint Log
Nama BackLog |  | Jumat | Sabtu | Minggu
Degree of Comparison |  | 25 | 0 | 0
Preposition |  | 25 | 25 | 0
Passive Voice Part I |  | 30 | 30 | 30
Passive Voice Part IV |  | 30 | 0 | 0
Concordance |  | 30 | 30 | 0
Elliptical Construction |  | 30 | 30 | 0
Subjunctive |  | 30 | 0 | 0
| Total = | 200 | 115 | 30

## 4.1
Burnt Down Chart Sprint 4 - Hari ke-10 s/d Hari ke-14
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Passive Voice Part I |  | 20 | 0 | 0 | 0
Passive Voice Part II |  | 30 | 0 | 0 | 0
Passive Voice Part III |  | 30 | 0 | 0 | 0
Passive Voice Part IV |  | 30 | 0 | 0 | 0
Gerund Vs To+Infinitive |  | 30 | 0 | 0 | 0
Memperbaiki Tampilan |  | 30 | 30 | 30 | 30
| Total = | 170 | 30 | 30 | 30

## 4.2
Burnt Down Chart Sprint 4 - Hari ke-10 s/d Hari ke-14
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Passive Voice Part I |  | 20 | 0
Passive Voice Part II |  | 30 | 0
Passive Voice Part III |  | 30 | 0
Passive Voice Part IV |  | 30 | 0
Gerund Vs To+Infinitive |  | 30 | 0
Memperbaiki Tampilan |  | 30 | 30
| Total = | 170 | 30

## 4.3
Burnt Down Chart Sprint 4 - Hari ke-10 s/d Hari ke-14
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Passive Voice Part I |  | 20 | 0 | 0
Passive Voice Part II |  | 30 | 0 | 0
Passive Voice Part III |  | 30 | 0 | 0
Passive Voice Part IV |  | 30 | 0 | 0
Gerund Vs To+Infinitive |  | 30 | 0 | 0
Memperbaiki Tampilan |  | 30 | 30 | 30
| Total = | 170 | 30 | 30

## 4.4
Burnt Down Chart Sprint 4 - Hari ke-10 s/d Hari ke-14
Sprint Log
Nama BackLog |  | Senin | Selasa | Rabu | Kamis
Passive Voice Part I |  | 20 | 0 | 0 | 0
Passive Voice Part II |  | 30 | 0 | 0 | 0
Passive Voice Part III |  | 30 | 0 | 0 | 0
Passive Voice Part IV |  | 30 | 0 | 0 | 0
Gerund Vs To+Infinitive |  | 30 | 0 | 0 | 0
Memperbaiki Tampilan |  | 30 | 30 | 30 | 30
| Total = | 170 | 30 | 30 | 30